## SPRINT BACKLOG
SPRINT [NUMBER] BACKLOG
ID | Role | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US001 | Leader | R coding | Tong Pak Yuen Isaac | Completed | 12 | Day 1: 2; Day 2: 3; Day 3: 4; Day 4: 2; Day 5: 1; Day 6: 0; Day 7: 0
US002 | Cooperator | Report writing (evaluation & conclution) | NG Ching Hei | Completed | 12 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 3; Day 6: 3; Day 7: 2
US003 | Cooperator | Report writing (code explanation) | Fu Lok Tim | Completed | 12 | Day 1: 0; Day 2: 0; Day 3: 4; Day 4: 4; Day 5: 3; Day 6: 1; Day 7: 0
[5 empty] | 36 | 2 | 3 | 8 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0